Project charter

One page, written before the plan. The sponsor signs section 9 and the project exists.

| Project name |  | Charter version |  |
| --- | --- | --- | --- |
| Sponsor |  | Project manager |  |
| Start date |  | Target finish |  |

1. Why this project, and why now

2. Objectives: how we will know it worked

| Objective | Measure | Target |
| --- | --- | --- |

3. Scope

| In scope | Out of scope (say it, or it creeps in) |
| --- | --- |

4. Milestones and deliverables

| Milestone | What exists when it is done | Date |
| --- | --- | --- |

5. Budget and people committed

6. Authority

| The project manager can decide alone | Goes to the sponsor |
| --- | --- |

7. Risks, assumptions and constraints

| Type | What it is | What we will do about it |
| --- | --- | --- |

8. Stakeholders

| Who | Why they care | How we keep them informed |
| --- | --- | --- |

9. Approval

| Name | Role | Signature | Date |
| --- | --- | --- | --- |

Project charter: example

An invented example for a small company. Delete this page when you are done with it.

| Project name | Move support to a new help desk | Charter version | 1.0 (approved) |
| --- | --- | --- | --- |
| Sponsor | Priya, head of operations | Project manager | Sam, support lead |
| Start date | 1 February 2027 | Target finish | 30 April 2027 |

1. Why this project, and why now

Support runs from a shared inbox. Requests get answered twice or not at all, and we cannot report on any of it. The renewal on our current email plan falls due in May, so this is the cheapest moment to change.

2. Objectives: how we will know it worked

| Objective | Measure | Target |
| --- | --- | --- |
| Stop requests going unanswered | Tickets with no first reply after 24 hours | Under 2% |
| Answer customers faster | Median time to first reply | Under 4 hours |
| Keep customers happy through the move | Post-ticket satisfaction score | No drop |

3. Scope

| In scope | Out of scope (say it, or it creeps in) |
| --- | --- |
| Choosing and setting up one help desk tool | Live chat and phone support |
| Moving the last 12 months of email history | History older than 12 months |
| Reply templates and training for the 6 agents | Changes to the refund policy |

4. Milestones and deliverables

| Milestone | What exists when it is done | Date |
| --- | --- | --- |
| Tool chosen | Signed order form | 19 Feb |
| Set up and tested | Inbox, templates and routing working | 19 Mar |
| Team trained | All 6 agents passed a practice run | 9 Apr |
| Live, inbox closed | Old address forwards to the tool | 30 Apr |

5. Budget and people committed

$9,000 for the first year of licences and setup. Sam at 50% for the 13 weeks; each agent 4 hours of training.

6. Authority

| The project manager can decide alone | Goes to the sponsor |
| --- | --- |
| Spending inside the budget, up to $1,000 at a time | Any cost that takes the project over $9,000 |
| Dates inside a milestone, if the milestone holds | Moving the 30 April go-live, or changing scope |

7. Risks, assumptions and constraints

| Type | What it is | What we will do about it |
| --- | --- | --- |
| Risk | History import loses attachments | Test with one month of mail by 5 March |
| Assumption | No new product launch before 30 April | Sam checks with Marketing every month |
| Constraint | Current email plan ends 31 May | Keep a four-week buffer after go-live |

8. Stakeholders

| Who | Why they care | How we keep them informed |
| --- | --- | --- |
| Support agents (6) | Their daily tool changes | Weekly stand-up |
| Finance | Refund reports come from the new tool | At each milestone |

9. Approval

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Priya | Sponsor | Priya (signed) | 28 Jan 2027 |
| Sam | Project manager | Sam (signed) | 28 Jan 2027 |