## RACI matrix
RACI matrix
One row per piece of work, one letter per person. Exactly one A per row, at least one R.
Piece of work | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Check
Free RACI matrix template from Templacity | [6 empty] | templacity.com

## Example
RACI matrix: website relaunch (example)
One row per piece of work, one letter per person. Exactly one A per row, at least one R.
Piece of work | Sponsor | Project lead | Designer | Developer | Marketing | Support | Check
Approve budget and launch date | A | R |  |  | C | I
Write the project brief | C | A/R | C | C | C
Design the new pages | I | A | R | C | C
Build and test the site |  | A | C | R |  | I
Write launch emails | I | A | C |  | R | C
Update help articles |  | A |  | C | C | R
Go / no-go decision | A | R | C | C | C | C
Post-launch review | I | A/R | C | C | C | C
Free RACI matrix template from Templacity | [6 empty] | templacity.com

## How to read it
How to read a RACI matrix
Letter | Means | Rule
R | Responsible | Does the work. One or more per row.
A | Accountable | Decides, and carries it if it goes wrong. Exactly one per row.
C | Consulted | Asked before the decision; their answer can change it. Keep it few.
I | Informed | Told after; cannot reopen it. As many as you like.
A/R | Accountable and responsible | One person both decides and does the work (small teams).
If you see | It means
Check says Two A | Nobody is really accountable. Pick one, out loud.
Check says No A | Worse, because the row looks finished.
Check says No R | Someone decides, nobody does it.
A column that is all C | Someone is in every conversation and owns nothing.
A row that is all I | Nobody is doing it. It is a backlog item, not a project line.
Free from Templacity: templacity.com